## Gantt Chart Template
GANTT CHART | [24 empty] | https://goo.gl/PXLbMe
| PROJECT TITLE | Cytotoxicity prediction toolbox (cytoxnet) |  | COMPANY NAME | [8 empty] | Zymergen
| PROJECT MANAGER |  |  | DATE
|  |  |  | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  |  | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Component specification |  | 100%
1.1 | use cases |  | 100% | bar: WEEK 1 M to WEEK 1 T
1.2 | package repo created and structured |  | 100% | bar: WEEK 1 W
1.3 | CI set up |  | 100% | bar: WEEK 1 R
1.4 | docs transcribed to repo |  | 100% | bar: WEEK 1 R
2 | Dataset compilation |  | 100%
2.1 | Exploratory dataset anlysis | All | 75%
2.1.1 | Initial descriptive statistcs | All | 75% | bar: WEEK 3 M to WEEK 3 F
2.1.2 | Guage overlap of datasets - PCA/UMAP | Rory | 0% | bar: WEEK 4 R to WEEK 5 F
2.1.3 | Find pool of non-toxic molecule data | Rory | 0% | bar: WEEK 4 R to WEEK 5 W
2.2 | Determine best practices for right-censored data |  | 0% | bar: WEEK 4 R to WEEK 6 M
2.3 | Compile doc with dataset availability | All | 0% | bar: WEEK 4 R to WEEK 6 F
3 | Pseudocode draft | All | 100%
4 | Load and pipeline found data automatically |  | 90%
4.1 | Load from csv in package data | Nida | 90% | bar: WEEK 2 F to WEEK 3 W
4.2 | Featurizing - Add more featurizers | Nida | 75% | bar: WEEK 2 F to WEEK 5 F
4.3 | Transforming | Rory | 90% | bar: WEEK 2 F to WEEK 3 W
4.4 | Splitting | Rory | 90% | bar: WEEK 2 F to WEEK 3 W
5 | Upload CSVs into GitHub and loadable in the package | Evan | 0% | bar: WEEK 4 R to WEEK 5 M
6 | test train models on example data | Evan | 100% | bar: WEEK 3 T to WEEK 12 F
6.1 | GPR, lasso, etc. | Evan | 100% | bar: WEEK 3 T to WEEK 3 F
6.2 | Graph CNN | Evan | 100% | bar: WEEK 3 R to WEEK 4 R
7 | Model training/analysis | All | 0% | bar: WEEK 4 M to WEEK 12 F
7.1 | Featurizing exploration | Nida | 0% | bar: WEEK 4 R to WEEK 5 F; WEEK 7 M to WEEK 12 F
8 | Transferring | All | 0% | bar: WEEK 4 M to WEEK 12 F
8.1 | Write transfer/pretrain functions | Evan | 0% | bar: WEEK 6 M to WEEK 6 F
8.2 | Test transferability between datasets | All | 0% | bar: WEEK 7 M to WEEK 9 F
9 | Compile results | All | 0%
9.1 | Create plots |  | 0% | bar: WEEK 9 M to WEEK 9 F
9.2 | Writeup |  | 0% | bar: WEEK 10 M to WEEK 10 F
9.3 | Presentation |  | 0% | bar: WEEK 10 M to WEEK 11 F

## Try Smartsheet
Try Smartsheet for Free