## Gantt Chart Template
GANTT CHART | [24 empty] | https://goo.gl/PXLbMe
| PROJECT TITLE | Cytotoxicity prediction toolbox (cytoxnet) |  | COMPANY NAME | [8 empty] | Zymergen
| PROJECT MANAGER |  |  | DATE
|  |  |  | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  |  | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Component specification |  | 100%
1.1 | use cases |  | 100% | bar: WEEK 1 M to WEEK 1 T
1.2 | package repo created and structured |  | 100% | bar: WEEK 1 W
1.3 | CI set up |  | 100% | bar: WEEK 1 R
1.4 | docs transcribed to repo |  | 100% | bar: WEEK 1 R
2 | Dataset compilation |  | 100%
3 | Pseudocode draft | All | 100%
4 | Load and pipeline found data automatically |  | 100%
4.1 | Load from csv in package data | Nida | 100% | bar: WEEK 2 F to WEEK 3 W
4.2 | Featurizing | Nida | 100% | bar: WEEK 2 F to WEEK 3 W
4.3 | Transforming | Rory | 100% | bar: WEEK 2 F to WEEK 3 W
4.4 | Splitting | Rory | 100% | bar: WEEK 2 F to WEEK 3 W
5 | test train models on example data | Evan | 100%
5.1 | GPR | Evan | 100% | bar: WEEK 3 T to WEEK 3 W
5.2 | Graph CNN | Evan | 100% | bar: WEEK 3 R to WEEK 3 F
6 | Model training/analysis | All | 100%
6.1 | Evaluation of Models and Features | All | 100%
7 | Transferring | All | 100%
7.1 | Write transfer/pretrain functions | Evan | 100% | bar: WEEK 6 M to WEEK 6 F
7.2 | Test transferability between datasets | All | 100% | bar: WEEK 7 M to WEEK 9 F
8 | Compile results | All | 80%
8.1 | Create plots | All | 70% | bar: WEEK 9 M to WEEK 10 T
8.2 | Class Presentation | All | 10% | bar: WEEK 10 M to WEEK 11 F
8.3 | Zymergen Presentation | All | 10% | bar: WEEK 10 M to WEEK 12 F

## Try Smartsheet
Try Smartsheet for Free